Security Misconfiguration Audit and Remediation ─────────────────────────────

PPM-002 Project Plan Timeline, Milestones, Deliverables, and Resource Allocation

| Prepared By | Ahmed Abdalrhman Ibrahim ¦ Yousef Osama ¦ Yousef Nasser |
| --- | --- |
| Prepared For | Internship Graduation Project — Security Engineering Program |
| Date | 10 May 2026 |
| Document Code | PPM-002 |
| Version | 1.0 — Final Release |
| Classification | Confidential — Internal & Academic Use Only |

1.  Document Purpose

This document presents the comprehensive execution plan for Project 10. It defines the project timeline through a structured Gantt chart, identifies the key milestones that govern phase transitions, catalogues all required deliverables with assigned ownership, and describes the allocation of personnel and technical resources across the four-week engagement period.

2.  Project Timeline Summary

| Project Commencement | Week 1 — Planning Phase and Laboratory Setup |
| --- | --- |
| Project Completion | Week 4 — Verification, Reporting, and Submission |
| Total Duration | Four (4) weeks |
| Graduate Deadline — Implementation | 17 May 2026 |
| Graduate Deadline — Final Reports | 24 May 2026 |

3.  Project Gantt Chart

The chart below represents the full project schedule. Active weeks are indicated by filled cells (██). Tasks spanning two consecutive weeks are marked active in both columns. Phases are colour-coded for visual clarity.

| Task / Deliverable | Project Phase | Wk 1 | Wk 2 | Wk 3 | Wk 4 |
| --- | --- | --- | --- | --- | --- |
| Target system selection and laboratory configuration | Phase 1 — Planning | ██ |  |  |  |
| Misconfiguration checklist compilation | Phase 1 — Planning | ██ |  |  |  |
| Project Planning & Management documents (PPM-001–005) | Phase 1 — Planning | ██ |  |  |  |
| Literature Review document (LR-001) | Phase 1 — Planning | ██ |  |  |  |
| Requirements Gathering documents (RQ-001–003) | Phase 1 — Planning | ██ |  |  |  |
| System Analysis & Design documents (SAD-001–005) | Phase 1 — Planning | ██ | ██ |  |  |
| Automated network scanning — Nmap, Nikto, OpenVAS | Phase 2 — Audit |  | ██ |  |  |
| Manual service inspection and credential testing | Phase 2 — Audit |  | ██ |  |  |
| Audit Findings Report (IMP-003) | Phase 2 — Audit |  | ██ |  |  |
| Impact Analysis Document (IMP-004) | Phase 2 — Audit |  | ██ |  |  |
| Remediation plan development | Phase 3 — Remediation |  |  | ██ |  |
| Configuration fix implementation | Phase 3 — Remediation |  |  | ██ |  |
| Fix Implementation Report (IMP-006) | Phase 3 — Remediation |  |  | ██ |  |
| Test Cases & Test Plan (TST-001) | Phase 3 — Remediation |  |  | ██ |  |
| Post-remediation re-scanning and verification | Phase 4 — Verification |  |  |  | ██ |
| Bug Report (TST-002) | Phase 4 — Verification |  |  |  | ██ |
| Final Project Report (FIN-001) | Phase 4 — Verification |  |  |  | ██ |
| User Manual and Project Presentation (FIN-002/003) | Phase 4 — Verification |  |  |  | ██ |
| GitHub final upload and README completion | Phase 4 — Verification |  |  |  | ██ |

| ■ Phase 1 — Planning | ■ Phase 2 — Audit | ■ Phase 3 — Remediation | ■ Phase 4 — Verification |
| --- | --- | --- | --- |

4.  Project Milestones

The following milestones define the formal completion criteria for each project phase. A milestone is considered achieved only when all associated deliverables have been completed, reviewed, and uploaded to the project repository.

| Ref. | Milestone | Target Date | Completion Criterion |
| --- | --- | --- | --- |
| MS-1 | Laboratory Operational and Planning Complete | End of Week 1 | Metasploitable2 confirmed reachable from Kali Linux; all planning, requirements, and design documents completed and committed to GitHub. |
| MS-2 | Active Audit Phase Complete | End of Week 2 | All checklist items assessed; Audit Findings Report and Impact Analysis Document finalised and uploaded to GitHub. |
| MS-3 | All Identified Misconfigurations Remediated | End of Week 3 | Every confirmed finding resolved; Remediation Plan, Fix Implementation Report, and Test Plan uploaded to GitHub. |
| MS-4 | Verification Passed and Project Formally Closed | End of Week 4 | Post-remediation scan confirms zero open findings; all final documents including report, PPT, and User Manual committed to GitHub. |

5.  Deliverables Register

The following register catalogues every project deliverable, its phase classification, document reference code, assigned primary owner, and target completion week.

| Deliverable | Phase | Doc Ref. | Primary Owner | Week |
| --- | --- | --- | --- | --- |
| Project Proposal | Planning | PPM-001 | Ahmed | 1 |
| Project Plan & Gantt Chart | Planning | PPM-002 | Ahmed | 1 |
| Task Assignment & Roles | Planning | PPM-003 | Ahmed | 1 |
| Risk Assessment & Mitigation Plan | Planning | PPM-004 | Yousef N | 1 |
| Key Performance Indicators (KPIs) | Planning | PPM-005 | Yousef N | 1 |
| Literature Review | Literature | LR-001 | Yousef O | 1 |
| Stakeholder Analysis | Requirements | RQ-001 | Yousef N | 1 |
| User Stories & Use Cases | Requirements | RQ-002 | Yousef N | 1 |
| Functional & Non-Functional Requirements | Requirements | RQ-003 | Yousef O | 1 |
| Problem Statement & Objectives | Design | SAD-001 | Ahmed | 1 |
| Software Architecture Document | Design | SAD-002 | Yousef O | 1 |
| Data Flow Diagram (DFD) | Design | SAD-003 | Yousef O | 1–2 |
| Activity & Sequence Diagrams | Design | SAD-004 | Yousef O | 1–2 |
| Technology Stack Document | Design | SAD-005 | Yousef O | 1 |
| Audit Target Selection Document | Implementation | IMP-001 | All | 1 |
| Misconfiguration Checklist | Implementation | IMP-002 | All | 1 |
| Audit Findings Report | Implementation | IMP-003 | Yousef O | 2 |
| Impact Analysis Document | Implementation | IMP-004 | Ahmed | 2 |
| Remediation Plan Document | Implementation | IMP-005 | All | 3 |
| Fix Implementation Report | Implementation | IMP-006 | Yousef O | 3 |
| Verification Report | Implementation | IMP-007 | All | 4 |
| Test Cases & Test Plan | Testing | TST-001 | Yousef N | 3 |
| Bug Report | Testing | TST-002 | Yousef N | 4 |
| Final Project Report | Final | FIN-001 | Ahmed | 4 |
| User Manual | Final | FIN-002 | Yousef N | 4 |
| Project Presentation (PPT/PDF) | Final | FIN-003 | All | 4 |

6.  Resource Allocation

The project operates exclusively within the team's available time and the tooling provided by the Kali Linux platform. No external budget or licensed software is required. The table below summarises the allocation of all human and technical resources.

| Ahmed Abdalrhman Ibrahim | Est. 12 hrs/week — project coordination, documentation management, report writing, GitHub administration |
| --- | --- |
| Yousef Osama | Est. 12 hrs/week — technical scanning, exploitation verification, remediation implementation, architecture documentation |
| Yousef Nasser | Est. 12 hrs/week — requirements analysis, risk documentation, test planning, presentation design |
| Kali Linux VM | Primary audit workstation — full Kali Linux toolset including Nmap, Nikto, Metasploit Framework, Hydra, Burp Suite, OpenVAS |
| Metasploitable2 VM | Audit target — operates continuously during audit and remediation phases; snapshots taken before each remediation session |
| VMware Workstation | Virtualisation host — manages both VMs and the isolated Host-Only network; installed on the team's Windows workstation |